## eb03
eb03 | inventory | p-vol | p-start | p-end | p-size | total | afr-op | html | docx | tei-p | tei-entry | comment | partial
r01 | 2018-03-17 | 15 | 770 | 799 | 30 |  | as | 2018-02-20 |  | 2017-07-20 | 2018-06-08 | begin 'r'
r01 | 2018-03-17 | 16 | 1 | 220 | 220 |  | as | 2018-02-20 |  | 2017-07-20 | 2018-06-08
r02 | 2018-03-17 | 16 | 221 | 469 | 249 |  | nn | 2018-02-20 |  | 2017-07-28 | 2018-06-08
r03 | 2018-03-17 | 16 | 470 | 579 | 110 |  | jk | 2018-02-20 |  | 2018-02-20 | 2018-06-08 | end 'r'
TOTAL-R | [5 empty] | 609
s01 | 2018-05-12 | 16 | 579 | 799 | 221 |  | rs |  | 2019-01-22 | 2019-02-14 | 2019-04-04 | begin 's'
s02 | 2018-05-12 | 17 | 1 | 225 | 225 |  | rs |  | 2019-01-22 | 2019-02-14 | 2019-04-06
s03 | 2018-05-12 | 17 | 226 | 450 | 225 |  | rs |  | 2019-01-22 | 2019-02-14 | 2014-04-12
s04 | 2018-05-12 | 17 | 451 | 675 | 225 |  | rs |  | 2019-01-22 | 2019-02-15 | 2019-04-19
s05 | 2018-05-12 | 17 | 676 | 827 | 152 |  | rs |  | 2019-01-22 | 2019-03-26 | 2019-04-27
s06 | 2018-05-12 | 18 | 1 | 150 | 150 |  | rs |  | 2019-01-22 | 2019-03-26 | 2019-04-27
s07 | 2018-05-12 | 18 | 151 | 267 | 117 |  | rs |  | 2019-01-24 | 2019-03-26 | 2019-04-27 | end 's'
TOTAL-S | [5 empty] | 1315
t01 | 2018-01-03 | 18 | 267 | 440 | 174 |  | rs |  | 2019-02-06 |  |  | begin 't'
t02 | 2018-01-03 | 18 | 441 | 614 | 174 |  | rs |  | 2019-03-22 |  |  | end 't'
TOTAL-T | [5 empty] | 348
uv01 | 2018-01-03 | 18 | 615 | 697 | 83 |  | rs |  |  |  |  | begin/end 'uv'
TOTAL-UV | [5 empty] | 83 | [6 empty] | 21
w01 | 2018-01-03 |  | 697 | 808 | 112 | [6 empty] | begin 'w'
w02 | 2018-01-03 |  | 809 | 919 | 111 | [6 empty] | end 'w'
TOTAL-W | [5 empty] | 223
x01 | 2018-01-03 |  | 919 | 923 | 5 | [6 empty] | begin/end 'x'
TOTAL-X | [5 empty] | 5
y01 | 2018-01-03 |  | 923 | 929 | 7 | [6 empty] | begin/end 'y'
TOTAL-Y | [5 empty] | 7
z01 | 2018-01-03 |  | 929 | 945 | 17 | [6 empty] | begin/end 'z'
TOTAL-Z | [5 empty] | 17
[12 empty] | 3/31/19 total | 2293
[6 empty] | 2607 | [5 empty] | rs total | 1684

## eb07
eb07 | inventory | p-vol | p-start | p-end | p-size | total | afr-op | html | docx | tei-p | tei-entry | comment | partial
r01 | 2018-03-17 | 19 | 1 | 250 | 250 |  | as | 2017-06-15 |  | 2018-05-22 | 2018-05-22 | begin 'r'; afr file deleted
r02 | 2018-03-17 | 19 | 251 | 500 | 250 |  | nn | 2017-07-13 |  | 2018-05-22 | 2018-05-22
r03 | 2018-03-17 | 19 | 501 | 594 | 94 |  | JK/pl | 2018-04-05 |  | 2018-05-22 | 2018-05-22 | end 'r'
TOTAL R | [5 empty] | 594
s01 | 2018-05-12 | 19 | 594 | 792 | 199 |  | tg |  | 2019-01-18 | 2019-02-19 | 2019-05-01 | begin 's'
s02 | 2018-05-12 | 20 | 1 | 225 | 225 |  | tg |  | 2019-01-18 | 2019-02-19 | 2019-05-06
s03 | 2018-05-12 | 20 | 226 | 450 | 225 |  | tg |  | 2019-01-18 | 2019-03-25
s04 | 2018-05-12 | 20 | 451 | 675 | 225 |  | tg |  | 2019-01-18 | 2019-03-26
s05 | 2018-05-12 | 20 | 676 | 848 | 173 |  | tg |  | 2019-01-18 | 2019-03-26
s06 | 2018-05-12 | 21 | 1 | 66 | 66 |  | tg |  | 2019-01-18 | 2019-03-26 |  | end 's'
TOTAL S | [5 empty] | 1113
t01 | 2019-01-28 | 21 | 66 | 255 | 190 |  | tg |  | 2019-02-08 |  |  | begin 't'
t02 | 2019-01-28 | 21 | 256 | 444 | 189 |  | tg |  | 2019-03-15 |  |  | end 't'
TOTAL T | [5 empty] | 379
u01 | 2019-01-28 | 21 | 445 | 533 | 89 |  | tg |  | 2019-03-22 |  |  | begin & end 'u'
TOTAL U | [5 empty] | 89
v01 | 2019-01-28 | 21 | 534 | 704 | 171 |  | tg |  | 2019-04-01 |  |  | begin & end 'v'
TOTAL V | [5 empty] | 171
w01 | 2019-01-28 | 21 | 705 | 953 | 249 |  | tg |  | 2019-04-29 |  |  | begin & end 'w'
TOTAL W | [5 empty] | 249
x01 | 2019-01-28 | 21 | 953 | 957 | 5 |  | tg |  |  |  |  | begin & end 'x'
TOTAL X | [5 empty] | 5
y01 | 2019-01-28 | 21 | 957 | 973 | 17 |  | tg |  |  |  |  | begin & end 'y'
TOTAL Y | [5 empty] | 17
z01 | 2019-01-28 | 21 | 974 | 1027 | 54 |  | tg |  |  |  |  | begin & end 'z'
TOTAL Z | [5 empty] | 54
[12 empty] | 3/31/19 total | 2346
[6 empty] | 2671 | [5 empty] | tg total | 1752

## eb09
eb09 | inventory | p-vol | p-start | p-end | p-size | total | afr-op | html | docx | tei-p | tei-entry | comment | partial
r01 | 2018-03-08 | 20 | 190 | 439 | 250 |  | as | 2018-03-07 |  | 2018-05-22 | 2018-05-24 | begin 'r'
r02 | 2018-03-08 | 20 | 440 | 689 | 250 |  | as | 2017-09-18 |  | 2018-05-22 | 2018-05-24
r03 | 2018-03-17 | 20 | 690 | 862 | 173 |  | jk | 2017-12-12 |  | 2018-05-22 | 2018-05-24
r03 | 2018-03-17 | 21 | 1 | 65 | 65 |  | jk | 2017-12-12 |  | 2018-05-22 | 2018-05-24
r04 | 2018-02-28 | 21 | 66 | 119 | 54 |  | bf | 2018-02-13 |  | 2018-05-22 | 2018-05-24 | end 'r'
TOTAL R | [5 empty] | 792
s01 | 2018-05-01 | 21 | 120 | 369 | 250 |  | bf |  | 2019-01-18 | 2019-02-10 |  | begin 's'
s02 | 2018-05-01 | 21 | 370 | 619 | 250 |  | bf |  | 2019-01-18 | 2019-02-12
s03 | 2018-05-01 | 21 | 620 | 856 | 237 |  | tg |  | 2019-01-18 | 2019-02-12
s04 | 2018-05-12 | 22 | 1 | 225 | 225 |  | tg |  | 2019-01-18 | 2019-03-26
s05 | 2018-05-12 | 22 | 226 | 450 | 225 |  | tg |  | 2019-01-18 | 2019-03-26
s06 | 2018-05-12 | 22 | 451 | 675 | 225 |  | tg |  | 2019-01-24 | 2019-03-26
s07 | 2018-05-12 | 22 | 676 | 856 | 181 |  | tg |  | 2019-01-18 | 2019-03-26 |  | eng 's'
TOTAL S | [5 empty] | 1593
t01 | 2019-01-22 | 23 | 1 | 238 | 238 |  | kr |  | 2019-04-01 |  |  | begin 't'
t02 | 2019-01-23 | 23 | 239 | 476 | 238
t03 | 2019-01-23 | 23 | 477 | 714 | 238 | [6 empty] | end 't'
TOTAL T | [5 empty] | 714
u01 | [11 empty] | total 3/31/19 | 2623
TOTAL U |  |  |  |  | 1 | [6 empty] | kr total | 238
[12 empty] | tg total | 1343
v01 |  |  |  |  | 1
TOTAL V
w01 |  |  |  |  | 1
TOTAL W
x01 |  |  |  |  | 1
TOTAL X
y01 |  |  |  |  | 1
TOTAL Y
z01 |  |  |  |  | 1
TOTAL Z | [11 empty] | u-z | 979

## eb11
eb11 | inventory | p-vol | p-start | p-end | p-size | total | afr-op | html | docx | tei-p | tei-entry | comment | partial
r01 | 2018-03-16 | 22 | 765 | 976 | 212 |  | pl | 2018-05-30 |  | 2018-05-30 | 2018-05-31 | begin 'r
r01 | 2018-03-16 | 23 | 1 | 38 | 38 |  | pl | 2018-05-30 |  | 2018-05-30 | 2018-05-31
r02 | 2018-03-16 | 23 | 39 | 288 | 250 |  | nn | 2017-09-11 |  | 2018-05-01 | 2018-05-18
r03 | 2018-03-16 | 23 | 289 | 520 | 232 |  | jk | 2017-11-01 |  | 2018-05-01 | 2018-05-17
r04 | 2018-03-13 | 23 | 521 | 758 | 238 |  | jk | 2018-02-28 |  | 2018-05-01 | 2018-05-17
r05 | 2018-02-28 | 23 | 759 | 952 | 194 |  | jk | 2018-02-14 |  | 2018-04-10 | 2018-05-09 | end 'r'
TOTAL R | [5 empty] | 1164
s01 | 2018-05-12 | 23 | 953 | 1024 | 72 |  | mh |  | 2019-01-24 | 2019-03-26 |  | begin 's'
s02 | 2018-05-12 | 24 | 1 | 225 | 225 |  | mh |  | 2019-01-24
s03 | 2018-05-12 | 24 | 226 | 450 | 225 |  | mh |  | 2019-01-24
s04 | 2018-05-12 | 24 | 451 | 675 | 225 |  | mh |  | 2019-01-24
s05 | 2018-05-12 | 24 | 676 | 900 | 225 |  | mh |  | 2019-01-24
s06 | 2018-05-12 | 24 | 901 | 1024 | 124 |  | mh |  | 2019-01-24
s07 | 2018-05-12 | 25 | 1 | 225 | 225 |  | mh |  | 2019-01-15
s08 | 2018-05-12 | 25 | 226 | 450 | 225 |  | mh |  | 2019-02-06
s09 | 2018-05-12 | 25 | 451 | 675 | 225 |  | mh | [5 empty] | 126
s10 | 2018-05-12 | 25 | 676 | 900 | 225 |  | tg |  | 2019-01-18
s11 | 2018-05-12 | 25 | 901 | 1064 | 164 |  | tg |  | 2019-01-18
s12 | 2018-05-12 | 26 | 1 | 225 | 225 |  | tg |  | 2019-01-18
s13 | 2018-05-12 | 26 | 226 | 320 | 95 |  | tg |  | 2019-01-18 |  |  | end 's'
TOTAL S | [5 empty] | 2480
t01 | 2018-12-03 | 26 | 321 | 569 | 248 |  | mh | [5 empty] | 72
t02 | 2018-12-03 | 26 | 570 | 817 | 248
t03 | 2018-12-03 | 26 | 818 | 1064 | 247
t04 | 2018-12-03 | 27 | 1 | 184 | 184
t05 | 2018-12-03 | 27 | 185 | 368 | 184
t06 | 2018-12-03 | 27 | 369 | 552 | 184
TOTAL T | [5 empty] | 1295
u01 | 2018-12-03 | 27 | 553 | 691 | 139
u02 | 2018-12-03 | 27 | 692 | 829 | 138
TOTAL U | [5 empty] | 277
v01 | 2018-12-10 | 27 | 830 | 1064 | 234
v02 | 2018-12-10 | 28 | 1 | 222 | 222
TOTAL V | [5 empty] | 456
w01 | 2018-12-10 | 28 | 223 | 442 | 220
w02 | 2018-12-10 | 28 | 443 | 661 | 219
w03 | 2018-12-10 | 28 | 662 | 880 | 219
TOTAL W | [5 empty] | 658
x01 | 2018-12-10 | 28 | 881 | 889 | 9
TOTAL X | [5 empty] | 9
y01 | 2018-12-10 | 28 | 890 | 947 | 58
TOTAL Y | [5 empty] | 58
z01 | 2019-12-10 | 28 | 948 | 1064 | 117
TOTAL Z | [5 empty] | 117
[12 empty] | total 3/31/19 | 3616
[6 empty] | 6514 | [5 empty] | mh total | 1744
[12 empty] | tg total | 709

## totals
Production | r-s-t | r-z
eb03 | 2272 | 2607
eb07 | 2086 | 2671
eb09 | 1506 | 2485
eb11 | 4939 | 6514
Total | 10803 | 14277
All pages | 62447 | 62447
% complete | 17.2995 | 22.8626
Production | completed by 3/31/19
eb03 | 2293
eb07 | 2346
eb09 | 2623
eb11 | 3616
TOTAL | 10878
All pages | 62447
% complete | 17.4196
Project gutenberg files
eb11 | vol. 2-17 (all) | a | 2036
|  | b | 1816
|  | c | 2770
|  | d | 1046
|  | e | 1281
|  | f | 1209
|  | g | 1346
|  | h | 1351
|  | i | 809
|  | j | 514
|  | k | 342
|  | l | 1178
|  | m | 1944
|  | raw total | 17642
|  | pages | 15553
eb11 to ocr
| eb11 total | 27732 | 100%
| pgb total | 15553 | 56.08%
| balance | 12179 | 43.92%

## issues
edition | type | ex-html-page | text
eb07 | blind-references | r03-0020 | RUMFORD, Count. See Thompson, Sir Benjamin.
eb07 | entry term in small-caps | r03-022 | Rupert's Drops
eb07 | entry term mixed cap/sc | r03-0024 | RUSHWORTH, John,
eb07 | poetry | r03-0025 | column 2
eb11 | cross-references in text | r01-0002 | (see Huguenots),
eb11 | cross-references in text | r01-0003 | (see Joinery and Masonry)
eb11 | cross-references in text | r01-0003 | (see Rodentia)
tables with multiple references to same note